## Sheet1
Work Estimation Details |  | Optimistic | Most Likely | Pessimistic | Confidence | 75% | 85% | 95% | 99.5% | Supporting Document Links: (Enter Links to Requirements, Specifications, or other supporting documents in this column)
SDLC Phases | Activity/Task (Requirement number) | Effort Hrs | Effort Hrs | Effort Hrs | Factor | Confidence | Confidence | Confidence | Confidence
Construction
| Coding based on priority |  |  |  | 0 | 0 | 0 | 0 | 0
| REQ 1 |  |  |  | 0 | 0 | 0 | 0 | 0
| Unique Areas | 7 | 9 | 12 | 0.83333 | 9.1667 | 10 | 10.8333 | 11.6667
| Game Saving UI | 1.5 | 2 | 3.5 | 0.33333 | 2.1667 | 2.5 | 2.8333 | 3.1667
| Game Saving UX | 1.5 | 2 | 4 | 0.41667 | 2.25 | 2.6667 | 3.0833 | 3.5
| Turn Based Combat | 7 | 9 | 11 | 0.66667 | 9 | 9.6667 | 10.3333 | 11
| Character Selection | 6 | 10 | 12 | 1 | 9.6667 | 10.6667 | 11.6667 | 12.6667
REQ 6
| REQ 7 |  |  |  | 0 | 0 | 0 | 0 | 0
| REQ 8 |  |  |  | 0 | 0 | 0 | 0 | 0
| REQ 9 |  |  |  | 0 | 0 | 0 | 0 | 0
| Setting Menu | 2.5 | 4 | 6 | 0.58333 | 4.0833 | 4.6667 | 5.25 | 5.8333
| Title Screen | 3 | 5 | 7 | 0.66667 | 5 | 5.6667 | 6.3333 | 7
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
Work Estimate Totals |  | 28.5 | 41 | 55.5 |  | 41.3333 | 45.8333 | 50.3333 | 54.8333